## Slide 1
Staging Beamline Layout
~2° from kicker and ~13° from septum
<number>
Kicker
EEX Dipole
~2.0 m
Septum
Dipole
~0.5 m
~2.0 m
Dipole
Spectrometer
=
Spect
Spect
Spect
Key:
Parts we need are in RED:
Septum
Kicker
Dipole
Quads (5-7 final)

## Slide 2
Parts List
New Hardware
Scott:
  kicker
  chamber before septum
IMP/Wei
  Septum
  Quads (5-7)
Jing?
  Waveguide
Standard Hardware
Nicole
  4 feedthroughs
  8? YAGS
  6 Crosses
  6 Actuators
  2 inch pipe
John?
  Dipole
Jing?
  Structures

## Slide 3
Overview Proposed Timeline 2017-2018
Month 2017 | Part | Work | Lead | Comments
May | Kicker | Septum | Fabrication | Scott, Wei | 
June |  |  |  |  | 
July | 
August | Kicker |  | Initial Testing | Nicole, Jing? | 
September |  |  | Installation | Eric?, Nicole | 
October | Septum |  | Initial Testing | Nicole | 
November |  |  | Installation | Eric?, Nicole | 
December | Kicker + Septum | Beam Test | Nicole | 
Month 2018 | Part | Work | Lead | Comments
January | PETS, Accel?, Quad, Dipole | Installation | Eric?, Jing?, Nicole | 
February | Full Beam Line Tests | Measurements | Nicole, Eric? | 
March | 
April |  |  |  | 
May |  |  |  | 

## Slide 4
Details Proposed Timeline May-June 2017
Month 2017 | Part | Work | Lead | Comments
May |  |  |  | 
Week 1 | FID Connector Arrives | Test Vacuum | Eric?, Nicole | Also waiting for septum
Week 2 | 
Week 3-4 | FID connector | Order 6 more | Scott?
Kicker, chamber | Finalize drawings and send out for fabrication | Scott?
June |  |  |  | 
Week 1-2 | Kicker, chamber | Send out parts for fabrication | Scott? | Also waiting for septum
Week 3-4 | Wait for parts | 

## Slide 5
Details Proposed Timeline July-Aug 2017
Month 2017 | Part | Work | Lead | Comments
July |  |  |  | 
Week 1-3 | Get HV supply from APS | Contact APS | Jing? | Waiting on parts
Week 4 | Beam Studies | Validate Linac Simulations | Nicole
August |  |  |  | 
Week 1-2 | Kicker Arrives | Initial bench Tests | Nicole, Jing or Shao? | Also waiting for septum
Week 3-4 | Begin Installation | Eric?, Nicole

## Slide 6
Details Proposed Timeline Sept-Oct 2017
Month 2017 | Part | Work | Lead | Comments
Sept |  |  |  |  |  | 
Week 1-2 | Kicker | Finish Installation | Eric?, Nicole | 
Week 3-4 | Beam Studies | Test Kicker, verify angle | Nicole | 
Oct |  |  |  |  |  | 
Week 1-2 | Septum Arrives? | Initial bench Tests | Nicole, Charles? | If Septum hasn’t arrived, installation of quads and wakefield structures after kicker can begin | 
Week 3-4 | Begin Installation | Eric?, Nicole |  | 

## Slide 7
Details Proposed Timeline Nov-Dec 2017
Month 2017 | Part | Work | Lead | Comments
Nov |  |  |  | 
Week 1-2 | Septum | Finish Installation | Eric?, Nicole | 
Week 3-4 | Beam Studies | Test septum, verify angle | Nicole | 
Dec |  |  |  | 
Week 1-2 | Beam Studies | Cont. kicker and septum tests. | Nicole | 
Week 3-4 | Christmas Holiday |  | 

## Slide 8
Details Proposed Timeline Jan-Feb 2017
Month 2017 | Part | Work | Lead | Comments
Jan |  |  |  |  |  | 
Week 1-2 | Quads, Dipole, Accelerating Structures | Installation |  | Eric?, Nicole |  | 
Week 3-4 |  |  |  |  | 
Feb |  |  |  |  |  | 
Week 1-2 | Beam Studies Power Measurements | Straight through w/ structures | Nicole | 
Week 3-4 | Beam Studies Power Measurements | Bent Beam line w/ structure | Nicole | 
March |  |  |  |  |  | 
Week 1-4 | Beam Studies | Full Beam Line | Nicole | 

## Slide 9
Back-UP

## Slide 10
Drift needed after kicker to get ∆x = 65 mm. i.e. 40 mm gap between beam edges | 2.29° 19.9 mm | 2.08° 18.1 mm
 | 1.6 m | 1.8 m
MeV | +/-20 kV | +/-25 kV | +/-30 kV
 | θ° | ∆x [mm] | θ° | ∆x [mm] | θ° | ∆x [mm]
75 | 1.53 | 13.3 | 1.91 | 16.6 | 2.29 | 19.9
70 | 1.64 | 14.2 | 2.04 | 17.8 | 2.45 | 21.4
65 | 1.76 | 15.3 | 2.20 | 19.2 | 2.64 | 23.0
60 | 1.91 | 16.6 | 2.39 | 20.8 | 2.86 | 24.9
55 | 2.08 | 18.1 | 2.60 | 22.7 | 3.13 | 27.2
50 | 2.29 | 19.9 | 2.86 | 24.9 | 3.44 | 29.9
Kicker Values